## Full Scope
EATCOOKJOY UAE — Full Scope of Work v0.4 ¦ May 2026
Chef App (B2B) + Consumer Platform (B2C) + UAE Operations + Marketing ¦ ★ = New in v0.4
KEY: |  | P0 – Launch Blocker | P1 – Pre-Beta | P2 – Scale Prep | v2 – Post-Launch | ★ New v0.4 | ⚠ OPEN | ✅ Resolved
Module | Sect | Feature | Description | Priority | Platform | UAE Note | Origin | Status | Open Question | Notes
CHEF APP (B2B)
CHEF APP (B2B) | 4.1 | Sign-in & First Run | Email, Google, Apple, Phone OTP (Twilio). Invite-only onboarding from ops.eatcookjoy.com. First-run checklist: profile → recipe → payout. | P0 | iOS + Android | OTP critical for UAE chefs without Google accounts | v0.2 | In spec | Biometric re-login (Face ID) not yet spec'd | Auth infra must be live before any chef can log in
CHEF APP (B2B) | 4.1 ★ | Onboarding Wizard | 3-step blocking wizard on first login: (1) Upload Emirates ID + food handler cert, (2) Set weekly availability defaults, (3) Add IBAN payout method. Steps 1 & 3 blocking — chef cannot accept bookings until complete. | P0 | iOS + Android | Dubai Municipality food handler cert required | v0.4 NEW | Missing — must add | Is food cert REQUIRED or encouraged? — OPEN | Regulatory risk if chefs operate without certification
CHEF APP (B2B) | 4.2 | Today (Home Screen) | Glanceable daily schedule. Hero card for next booking: client, time, location, guest count, menu title. New-booking alert banner. Offline cached data indicator. Empty state: 'No bookings today — get discovered' CTA. | P0 | iOS + Android | Arabic RTL on all states required | v0.2 | In spec | — | Most critical screen — must nail all states
CHEF APP (B2B) | 4.2 ★ | Allergen Warning Badge | Red safety badge on Today hero card if any booking today has a critical allergy (nuts, gluten, shellfish, dairy). Cannot be collapsed. Tapping opens allergen detail. Halal flag also shown (UAE-specific). | P0 | iOS + Android | Halal flag required for UAE market | v0.4 NEW | Missing — must add | — | Safety-critical; legal liability if missed
CHEF APP (B2B) | 4.2 ★ | Earnings Widget | 'This week: AED X earned / AED Y pending' summary card on Today screen. One-tap to full earnings screen. Motivates daily engagement and chef retention. | P1 | iOS + Android | AED currency; AED formatting | v0.4 NEW | Missing — fast add | — | Benchmarked from Sous and Yhangry
CHEF APP (B2B) | 4.3 | Booking Detail | Full booking view: header (date/time/status), location map pin, client contact, attendees + per-person dietary, menu summary, prep & cook schedule (AI-generated, editable time-anchored tasks), close-out (mark done + photo upload). Cancellation state + policy display. | P0 | iOS + Android | Emirates-level location; Arabic address format | v0.2 | In spec | Prep schedule editable — RESOLVED: Yes | Core daily workflow screen
CHEF APP (B2B) | 4.3 ★ | Grocery List Shortcut | Auto-generated ingredient list for this booking (recipe ingredients × guest count). Chef can share via WhatsApp or screenshot. No ordering in v1 — list only. Arabic ingredient names from ECJ vault. | P2 | iOS + Android | Arabic ingredient names from UAE recipe vault | v0.4 NEW | Missing — fast add | — | Saves chef 20–30 min prep time per booking
CHEF APP (B2B) | 4.3 ★ | Dispute / Issue Report | 'Report a problem' button available after booking completion. Chef selects reason (late client, unsafe premises, allergy undisclosed, other) + free text. Routes to ECJ ops via WhatsApp or in-app form within 2 hrs. | P1 | iOS + Android | — | v0.4 NEW | Missing — must add | — | No current mechanism for chef to flag issues
CHEF APP (B2B) | 4.3 ★ | Recurring Client History | Collapsible 'Client history' section in Booking Detail for returning clients. Last 3 visits, menus cooked, ratings given, persistent dietary notes carried forward. 'Repeat guest ♻' badge on Today hero card. | P2 | iOS + Android | — | v0.3 DB-10 | Needs spec | Privacy policy for client data storage | Long-term relationships generate 3–5× annual earnings per chef
CHEF APP (B2B) | 4.4 | Earnings & Payouts | Summary: total paid-to-date + pending. Per-booking list: gross, ECJ fee (%), net. Payout method on file. Monthly trend chart. Commission transparency line: 'ECJ fee: 20% = AED X. Your net: AED Y.' Export PDF monthly summary. | P1 | iOS + Android | IBAN payout (UAE banks); AED currency | v0.2 | In spec | Commission rate not yet set — OPEN | Trust surface — must never be ambiguous
CHEF APP (B2B) | 4.4 ★ | Fast Payout Toggle | 'Next-day payout (2.5% fee)' vs 'Weekly (free)'. Selectable globally in Settings or per-booking at close-out. Fee deducted transparently. Confirmation dialog before enabling. | P1 | iOS + Android | UAE bank IBAN processing time to be confirmed | v0.3 DB-05 | Needs spec | UAE bank next-day processing confirmed? — OPEN | Yhangry yPay is #1 chef satisfaction driver
CHEF APP (B2B) | 4.4 ★ | Cancellation Protected Payout | Special payout line when booking cancelled inside protection window. Shows: 'Protected payout — client cancelled within 24 hrs — AED X guaranteed.' Push notification triggered. Visible in earnings list. | P1 | iOS + Android | — | v0.3 DB-06 | Needs spec | Protection policy not finalised — OPEN | Policy: 100% <24 hrs, 50% 24–48 hrs (recommended)
CHEF APP (B2B) | 4.4 ★ | Earnings PDF Export | 'Download earnings summary (AED, by month)' — generates clean PDF for UAE visa renewal and bank statement proof. Not a tax document — income summary only. Available from Earnings screen. | P2 | iOS + Android | UAE freelance visa income proof requirement | v0.4 NEW | Missing — add | — | High demand from freelance chef segment in UAE
CHEF APP (B2B) | 4.5 | Profile (Editable) | Photo, name, headline, bio, cuisines, service area by emirate, sample menus, photo gallery, languages spoken (Arabic/English/Filipino/Hindi/Urdu), profile completeness score with tips, pricing/rate field, social links (Instagram, TikTok). | P1 | iOS + Android | Languages field critical for UAE multicultural market | v0.2 | In spec | — | Directly powers the public profile page
CHEF APP (B2B) | 4.5 ★ | Chef Pricing / Rate Field | Chef sets standard rate: fixed (AED/session) or range (AED X–Y). Optional note: 'Rate includes grocery shopping'. Shown on public profile so clients know indicative cost before booking. | P1 | iOS + Android | AED pricing; session-based (not hourly) is UAE norm | v0.4 NEW | Missing — must add | — | No pricing field currently spec'd anywhere in v0.1–v0.3
CHEF APP (B2B) | 4.5 ★ | Ratings & Reviews Display | Aggregate star rating + review count on profile (e.g. ★ 4.8 • 23 reviews). Most recent 3 reviews shown. Fed by 4.15 review trigger. Visible on both chef-side profile and public page. | P0 | iOS + Android | — | v0.3 DB-04 | Needs spec (links to 4.15) | — | Most universal trust signal across all 20 competitors
CHEF APP (B2B) | 4.5 ★ | Instagram / TikTok Links | Chef adds their social handles in Profile settings. Displayed as clickable icons on public profile page. Cross-promotes ECJ through chef's existing social following. | P1 | iOS + Android | UAE food discovery is heavily social (IG, TikTok) | v0.4 NEW | Missing — easy add | — | EAZ Chef built 35K+ followers — ECJ should leverage chefs' audiences
CHEF APP (B2B) | 4.6 | Public Profile Sharing | Shareable public link (eatcookjoy-uae.com/chef/ahmed). WhatsApp one-tap share with pre-filled template. QR code for in-person sharing. Profile analytics: views, clicks, bookings originated from profile. | P1 | iOS + Android + Web | WhatsApp is UAE's dominant sharing channel | v0.2 | In spec | Public link routing — RESOLVED: Book + Message CTAs | Chef's personal brand URL
CHEF APP (B2B) | 4.6 ★ | Chef-Branded Subdomain | chef-ahmed.eatcookjoy-uae.com — unique URL per top chef. Wildcard DNS routing. Arabic SEO benefit. Link from public profile and chef app. First 20 Founding Chefs receive subdomain as perk. | v2 | Web | Arabic SEO benefit for UAE chef name searches | v0.3 DB-08 | Post-launch | — | V2 after 20+ chefs onboarded; nginx wildcard subdomain routing
CHEF APP (B2B) | 4.7 | Recipe Library | List/grid of chef's saved recipes. Detail: ingredients, steps, yield, timing, allergen tags. Create/edit/delete. Link recipe to booking menu. Hands-free step-by-step cook mode (large type, voice-over optional). Servings auto-scaling. Import from URL or paste. | P2 | iOS + Android | Arabic recipe names; Khaleeji/Gulf cuisine collection in vault | v0.2 | In spec | — | Referenced during cooking — large type, one-handed operation
CHEF APP (B2B) | 4.7 ★ | ECJ Recipe Vault Integration | Chef browses the 16,848-recipe ECJ vault and saves to personal library. Search by cuisine, dietary profile, occasion. Allergen cross-check: if saved recipe conflicts with confirmed booking allergy → red alert. Strongest ECJ technical differentiator vs all competitors. | P1 | iOS + Android | Arabic recipes for UAE/Gulf cuisine | v0.4 NEW | Missing — must add | API connection to main ECJ platform vault required | 16,848-recipe vault is ECJ's biggest moat — must expose in chef app
CHEF APP (B2B) | 4.8 | Client Preview Mode | Chef toggles into read-only 'client view' of their own public profile. Persistent 'Preview mode' banner prevents confusion. Exit via X. RTL preview must match actual Arabic client experience. | P2 | iOS + Android | Arabic RTL preview must be accurate | v0.2 | In spec | Preview vs QA — RESOLVED: chef-facing preview only | Helps chef optimise their own public profile
CHEF APP (B2B) | 4.9 | Message Client | In-app per-booking message thread. Text only in v1. Quick replies: 'On my way', 'Running late', 'Door code?', 'Prep done'. Pinned dietary/access info strip above thread. Push notification on new message. Thread open 72 hrs post-completion; read-only 30 days; then archived. | P1 | iOS + Android | WhatsApp handoff as secondary option, not default | v0.2 | In spec | Thread lifespan — RESOLVED | Protects chef's personal phone number
CHEF APP (B2B) | 4.9 ★ | Pre-Booking Video Call | 'Request video call' CTA in message thread. Min viable v1: WhatsApp Video deep-link. In-app WebRTC video is v2. Chef receives notification. Client tap from public profile page also triggers this flow. | P1 | iOS + Android | WhatsApp Video is UAE-dominant video call method | v0.3 DB-02 | Needs spec (4.18) | — | ChefMaison's #1 UAE conversion feature
CHEF APP (B2B) | 4.9 ★ | AI Suggested Replies | Claude-powered reply suggestions for common client questions. Chef taps to send or edits first. Toggle on/off in settings. Arabic language suggestions required. Reduces typing while in kitchen or driving. | P1 | iOS + Android | Arabic language reply suggestions essential | v0.3 DB-03 | Part of 4.14 AI Assist | — | Saves 5–10 min per booking conversation
CHEF APP (B2B) | 4.10 | Booking Accept / Decline | Request card: client name, date/time, emirate, menu title, guest count, payout preview (gross/ECJ fee/net). Accept (green) / Decline (reason code pick-list: 'not available', 'outside area', 'other'). 2-hr response timer. Dietary summary shown before accepting. Counter-proposal (alt time) is v2. | P0 | iOS + Android | Emirate field; Arabic menu display | v0.2 | In spec — needs full screen spec | Counter-proposal not yet spec'd — v2 | P0 blocker — without this no bookings can be accepted
CHEF APP (B2B) | 4.11 | Notifications (12 types) | Push notifications: 1) New booking request, 2) Booking confirmed, 3) Booking cancelled by client, 4) Booking reminder 24h, 5) Reminder 2h before, 6) New client message, 7) Payout paid, 8) Profile review result, 9) Cancellation protection triggered, 10) Review received, 11) Profile view spike, 12) Video call request. All deep-link. Per-type toggle. | P1 | iOS + Android | Arabic push notification text | v0.2 + v0.4 adds types 9–12 | In spec (extended v0.4) | — | v0.4 adds 4 new types vs v0.2
CHEF APP (B2B) | 4.12 | Settings (Full) | Payout method (IBAN + schedule + fast payout), notification preferences, availability defaults, minimum booking notice (1h/2h/4h/24h), travel radius by emirate, profile visibility (on/off), language (AR/EN), documents & verification upload, commission rate display, help & support, log out / delete account. | P1 | iOS + Android | IBAN UAE banks; Arabic language toggle; Emirates ID upload | v0.2 + v0.4 | In spec (extended v0.4) | — | v0.4 adds: commission display, document upload, min notice, travel radius
CHEF APP (B2B) | 4.13 | Availability / Calendar | Weekly availability grid (tap time blocks). Date-range blocks with reason. Read-only overlay of existing bookings (green=accepted, amber=pending, grey=blocked). 'Pause all new bookings' toggle. Google Calendar sync. Recurring availability pattern. Hijri/Islamic calendar awareness for Ramadan. | P2 | iOS + Android | UAE Hijri calendar awareness for Ramadan prep period | v0.2 + v0.4 | In spec (extended v0.4) | — | v0.4 adds: Google Calendar sync, recurring pattern, Hijri awareness
CHEF APP (B2B) | 4.14 ★ | AI Assist (Claude-Powered) | Menu builder: cuisine + dietary + guests + budget → AI suggests 3-course menu from ECJ vault. Prep schedule generator: booking time + menu → time-anchored task list. Quote generator: generate suggested price for custom event. Suggested replies (4.9). All AI output editable. 'Generated by AI' label always visible. | P1 | iOS + Android | Arabic AI output; Khaleeji cuisine in vault | v0.3 DB-03 + v0.4 | New screen — needs full spec | Claude API integration scope and budget — OPEN | Chefs take 30–40% more bookings with AI assist (Yhangry benchmark)
CHEF APP (B2B) | 4.15 ★ | Client Rating & Review Trigger | Auto-triggers rating request to client (WhatsApp + consumer app) within 30 min of chef marking booking 'done'. 5-star scale + optional 200-char text. ECJ moderation before publishing. Ratings appear on chef profile (4.5). Chef sees new review notification (type 10). Streak badge on Today. | P0 | iOS + Android + WhatsApp | Arabic rating request message required | v0.3 DB-04 + v0.4 | New screen — needs full spec | — | CRITICAL — without it profiles have zero trust signal at launch
CHEF APP (B2B) | 4.16 ★ | Cancellation Protection Display | Shows protection status on: booking detail, accept screen, earnings. Policy badge: 100% if client cancels <24 hrs; 50% if 24–48 hrs; 0% if >48 hrs. Push notification type 9 when triggered. 'Protected payout' line in earnings view. | P1 | iOS + Android | AED amounts; UAE consumer protection law alignment | v0.3 DB-06 + v0.4 | New screen — needs full spec | Policy % not yet set — OPEN | Suppresses chef attrition from cancellation risk
CHEF APP (B2B) | 4.17 ★ | Chef Video Introduction Upload | 30–60s selfie video (record in-app or pick from camera roll). ECJ ops reviews before going live. Inline autoplay (muted, looping) on public profile. In-app tips for a great video. States: No video / Pending review / Approved / Rejected (with reason). | P1 | iOS + Android | Arabic language option in video intro | v0.3 DB-01 + v0.4 | New screen — needs full spec | — | Sous (US): video profiles convert significantly higher than photo-only
CHEF APP (B2B) | 4.18 ★ | Pre-Booking Video Call Screen | Client taps 'Meet [Chef Name] first' on public profile. Chef receives notification (type 12). Chef accepts → min viable: WhatsApp Video deep-link. In-app WebRTC is v2. Status: Requested / Accepted / Missed / Completed. | P1 | iOS + Android + Web | WhatsApp Video — UAE standard | v0.3 DB-02 + v0.4 | New screen — needs full spec | — | ChefMaison: highest-rated feature in UAE; converts browse to book
CHEF APP (B2B) | 4.19 ★ | Insurance & License Badge | Chef uploads 4 document types: (1) Food Handler Cert, (2) Freelance License, (3) Emirates ID, (4) Liability Insurance. ECJ ops verifies within 48 hrs. Verified badge icons on public profile. Expiry auto-flag 30 days before. Emirates ID + Food Cert REQUIRED before bookable. Insurance encouraged. | P1 | iOS + Android | Dubai Municipality cert; UAE freelance license | v0.3 DB-07 + v0.4 | New screen — needs full spec | Which docs are REQUIRED vs encouraged? — OPEN | Critical UAE trust signal: clients invite chefs into their homes
CONSUMER PLATFORM (B2C)
CONSUMER PLATFORM (B2C) | C-01 ★ | Chef Discovery & Search | Browse and filter chefs: cuisine type, dietary speciality (11 profiles incl. Halal), emirate, date availability, price range, rating, languages spoken. Chef cards show photo, name, star rating, price, cuisines, distance. Recommended chefs at top. Arabic and English search. | P0 | Web + iOS + Android | Emirate filter; Halal/dietary filters; Arabic UI | v0.4 NEW | No spec — must create | Search ranking algorithm not defined — OPEN | Without this, no demand channel exists
CONSUMER PLATFORM (B2C) | C-02 ★ | Booking Flow (8-Step) | (1) Service type: Weekly Prep / Dinner Party / Special Event. (2) Date + time + emirate + venue type (apartment/villa/yacht/hotel suite). (3) Guest count. (4) Cuisine preference. (5) Allergen + dietary form (11 profiles, per-guest). (6) Menu: select from chef's menus or 'leave to chef'. (7) Review + payment. (8) Confirmation. | P0 | Web + iOS + Android | Venue type: apartment/villa/yacht/hotel suite (UAE-specific) | v0.4 NEW | No spec — must create | Payment gateway not selected — OPEN | Every AED flows through this flow — most critical build
CONSUMER PLATFORM (B2C) | C-03 ★ | Payment Gateway | Card (Visa/Mastercard), Apple Pay, Google Pay, Samsung Pay. Recommended providers: Telr, PayTabs, or Network International. 3DS authentication. AED settlement. Refund handling for cancellations per policy (C-08). No cross-border fees for UAE cards. | P0 | Web + iOS + Android | UAE card schemes; AED settlement; 3DS required by UAE banks | v0.4 NEW | No spec — OPEN | Provider not selected — OPEN | P0 blocker — no monetisation without payment
CONSUMER PLATFORM (B2C) | C-04 ★ | Booking Confirmation & Notifications | Immediate: WhatsApp + email confirmation (both required). Calendar invite attachment (Google/Apple). 24h reminder WhatsApp + push. Chef assigned notification. Chef profile link in confirmation. Change/cancel CTA. Arabic WhatsApp template required. | P0 | WhatsApp + Email + Push | Arabic WhatsApp confirmation template required | v0.4 NEW | No spec — must create | WhatsApp Business API account required — OPEN | UAE clients expect WhatsApp confirmation, not just email
CONSUMER PLATFORM (B2C) | C-05 ★ | Client Dashboard | Past bookings with chef photos from close-out. Upcoming bookings with countdown timer. Favourite chefs list. Saved dietary profiles (per guest). Rating history. Referral credits balance. 'Book again' CTA on past bookings. | P1 | Web + iOS + Android | Arabic UI; AED pricing throughout | v0.4 NEW | No spec — must create | — | Repeat bookings start from the client dashboard
CONSUMER PLATFORM (B2C) | C-06 ★ | Allergen & Dietary Profile (Consumer) | Client completes 11-profile dietary assessment. Per-guest profiles for groups (e.g., 'Guest 2: nut allergy, vegetarian'). Saved and auto-filled for future bookings. Auto-cross-checked against chef's assigned recipes — allergen conflict alert before confirming booking. Halal certification field. | P0 | Web + iOS + Android | Halal certification — UAE-specific required field | v0.4 NEW | No spec — must create | — | Safety-critical — links to chef recipe allergen check in 4.7
CONSUMER PLATFORM (B2C) | C-07 ★ | Client Review Submission | 5-star rating + 200-char text after each completed booking. Triggered by chef's 'Mark done' action (4.15). Sent via WhatsApp CTA (primary) + in-app prompt. ECJ moderates before publishing to chef public profile. Review response from chef is v2. | P0 | WhatsApp + Web | Arabic review option; right-to-left text input | v0.4 NEW | No spec — must create | — | Connects directly to 4.15 on chef side
CONSUMER PLATFORM (B2C) | C-08 ★ | Cancellation & Refund Policy | Client-facing: full refund if >48 hrs notice; 50% if 24–48 hrs; no refund if <24 hrs (chef's cancellation protection triggers). Shown at: checkout summary, booking confirmation, client dashboard. UAE Consumer Protection Law alignment required. | P0 | Web + WhatsApp | UAE Consumer Protection Law compliance required | v0.4 NEW | Policy % not finalised — OPEN | Policy not set — OPEN | MonChef: 48-hr full refund is UAE market benchmark
CONSUMER PLATFORM (B2C) | C-09 ★ | WhatsApp 'Book a Chef' Button | Sticky floating WhatsApp CTA button on every page. Pre-filled message: 'Hi EatCookJoy, I'd like to book a private chef for [occasion].' Routes to ECJ WhatsApp Business account. Human or AI first response within 2 hrs. | P0 | Web | UAE consumers default to WhatsApp for ALL service enquiries | v0.4 NEW | No spec — easy add | WhatsApp Business API required — OPEN | Highest-converting UAE acquisition touchpoint across all service categories
CONSUMER PLATFORM (B2C) | C-10 ★ | Referral Programme | 'Refer a client, get AED 50 credit.' Unique referral link per client. Credit applied to next booking automatically. Referred client gets AED 25 off first booking. Tracked via referral code. Dashboard shows referral balance and history. | P1 | Web + WhatsApp | AED credits — no cash payout needed | v0.4 NEW | No spec — must design | — | Word-of-mouth is highest-converting acquisition in UAE premium services
CONSUMER PLATFORM (B2C) | C-11 ★ | Seasonal / Occasion Landing Pages | Dedicated pages: Ramadan Iftar Chef, Eid Al Adha Family Feast, Dubai National Day Dinner, New Year Private Dining, Valentine's Day. Curated menus per occasion, seasonal chef recommendations, pre-built booking CTA. SEO-optimised URLs. | P1 | Web | UAE Islamic + national calendar events — high-intent seasonal traffic | v0.4 NEW | No spec — must create | — | Captures seasonal demand at zero additional marketing cost
CONSUMER PLATFORM (B2C) | C-12 ★ | Corporate / Event Package Page | 'For your company / event' dedicated page. Packages from AED 150/head. Team lunches, client entertainment, C-suite dinners, product launches. Enquiry form routes to ECJ ops for custom quote. DIFC, Business Bay, JLT geographic targeting. | P2 | Web | UAE corporate entertainment culture — DIFC, Business Bay, JLT | v0.4 NEW | No spec — must create | — | Zen Cook Finder already targets HoReCa B2B — ECJ must compete
OPS & LEGAL
OPS & LEGAL | OL-01 ★ | UAE Trade License (Marketplace) | Register ECJ as LLC or Free Zone company. Activity codes: technology platform, food marketplace, chef placement. Options: DED mainland or DMCC/DIFC free zone. Cost: AED 15,000–50,000. Timeline: 2–4 weeks. Required before payment gateway and hiring. | P0 | Ops | UAE Commercial Companies Law; DED or DMCC | v0.4 NEW | Status unknown — OPEN | Free zone vs mainland? — OPEN | P0 blocker for payment gateway integration and legal operation
OPS & LEGAL | OL-02 ★ | Published Commission Rate | Publicly post commission on 'Cook with ECJ' chef recruitment page. Recommended: 20% standard; 15% for chefs with 10+ reviews. Transparency is #1 chef recruitment driver. Must be set before chef onboarding campaign launches. | P0 | Web | — | v0.4 NEW | Decision required — OPEN | Rate not yet set — OPEN | Take a Chef: 20%; Shef (US): 15% — ECJ must be competitive
OPS & LEGAL | OL-03 ★ | T&C & Privacy Policy (Arabic + English) | Consumer T&Cs: booking, cancellation (48-hr full refund), payment, data use, liability. Chef T&Cs: commission %, payout schedule, code of conduct, termination. Arabic mandatory under UAE Consumer Protection Law. PDPL compliance for data storage. | P0 | Web | UAE PDPL compliance; Arabic language legally required | v0.4 NEW | Does not exist — must create | — | Legal requirement before first consumer booking can be accepted
OPS & LEGAL | OL-04 ★ | IBAN Payment Infrastructure | Integrate payment processor (Telr / PayTabs / Network International) for: (a) client card payments at checkout, (b) chef IBAN payouts weekly + next-day. UAE SWIFT/IBAN connectivity. 3DS authentication. AED-only transactions. Integration timeline: 4–6 weeks. | P0 | Tech/Ops | UAE bank IBAN scheme; AED-only settlement | v0.4 NEW | Not built — OPEN | Provider selection timeline — OPEN | P0 blocker — no monetisation without this
OPS & LEGAL | OL-05 ★ | Chef Vetting & Approval Pipeline | Application form (ops.eatcookjoy.com) → ECJ ops review → document check (Emirates ID, food cert, optional freelance license) → background validation → approved → SMS/WhatsApp invite → app sign-in. Target: <48 hrs application-to-bookable. First 50: manual review. Then: automated OCR. | P0 | Ops + Web | Dubai Municipality food handler cert verification | v0.4 NEW | Not operationalised — must build | Manual or automated verification? — OPEN | Without pipeline, chef supply cannot be built
OPS & LEGAL | OL-06 ★ | Liability & Insurance Framework | Define liability for: chef injury in client's home, allergic reaction from undisclosed allergy, property damage, food poisoning. Options: (a) require individual chef liability insurance (upload in 4.19) or (b) ECJ group policy covering all chefs. Publish clear liability clause in T&Cs. | P0 | Legal/Ops | UAE tort law and domestic premises liability | v0.4 NEW | Not defined — OPEN | ECJ group policy vs individual requirement? — OPEN | Legal exposure before first booking if undefined
OPS & LEGAL | OL-07 ★ | WhatsApp Business API Setup | ECJ WhatsApp Business account for: booking confirmations (C-04), rating requests (4.15), cancellation alerts, chef onboarding OTP, customer support. Meta Business Manager setup. Apply for green tick verification. Template message approval from Meta required. | P0 | Ops/Tech | UAE's #1 communication channel — essential infrastructure | v0.4 NEW | Not set up — must do | — | Required for consumer notifications, OTP, and all WhatsApp flows
OPS & LEGAL | OL-08 ★ | Customer Support Structure | Support channels: WhatsApp Business (primary, <2 hr SLA), email (secondary, <24 hr). Escalation path: booking disputes → ops, allergic reactions → emergency ops + legal, chef no-shows → immediate rebook + compensation, payment issues → finance. Arabic support required. | P1 | Ops/Web | Arabic support required; UAE client expectations are high | v0.4 NEW | Not defined — must build | Human or AI chatbot for first tier? — OPEN | No support structure = no trust for premium UAE clients
OPS & LEGAL | OL-09 ★ | Chef Quality Standards Document | Published document (PDF + web page): hygiene certification required, professional appearance standards, on-time arrival policy (<15 min late = booking credit), allergen protocol (mandatory disclosure check), equipment policy (chef brings own knives/aprons), conduct code (no phones at table, no food photography without permission). | P1 | Web/Ops | Dubai Municipality food safety standards alignment | v0.4 NEW | Does not exist — must write | — | Builds client trust; sets chef expectations before first booking
OPS & LEGAL | OL-10 ★ | Post-Service NPS Survey | 2-question NPS sent 24 hrs after service via WhatsApp: (1) 'How likely to recommend ECJ? (0-10)' and (2) 'What could we improve?' Auto-segments promoters for referral ask. Target NPS >60 in first 3 months. Weekly tracking in simple ops dashboard. | P1 | WhatsApp/Ops | Arabic NPS survey option | v0.4 NEW | Not defined — must build | — | Leading indicator of product-market fit before scaling
MARKETING & GROWTH
MARKETING & GROWTH | MG-01 ★ | Instagram (@eatcookjoyuae) | Create and activate ECJ UAE Instagram. 3+ posts per week: chef profiles, behind-the-scenes kitchen content, finished dishes, client reactions (with permission), recipe inspiration. Heavy Reels (3× reach vs static). Arabic captions + English. UAE food hashtags. Stories for daily engagement. | P0 | Social/Marketing | Arabic captions; UAE food hashtags (#dubaifoodies etc) | v0.4 NEW | Not active — must launch | — | EAZ Chef: 35K; Hello Chef: 54K followers — ECJ must close this gap
MARKETING & GROWTH | MG-02 ★ | TikTok (@eatcookjoyuae) | Create and activate ECJ UAE TikTok. 5+ posts per week at launch: 'what I cooked for a Dubai family today', chef transformation videos, kitchen prep ASMR, client reveal reactions. Organic virality possible with zero paid spend. 100K target in 6 months. | P0 | Social/Marketing | UAE Gen Z and expat food discovery on TikTok | v0.4 NEW | Not active — must launch | — | Fastest-growing food content channel in UAE 2025–26
MARKETING & GROWTH | MG-03 ★ | Influencer Campaign (5 Micro-Influencers) | Partner with 5 UAE food influencers (20K–100K followers). Each hosts dinner cooked by an ECJ Founding Chef. Documents full experience (Stories + Reel). Budget: AED 2,000–5,000 per influencer. Total: AED 10,000–25,000. Timeline: first 6 weeks after launch. | P1 | Marketing | Dubai-based food influencers with GCC-majority audiences | v0.4 NEW | Not started — must plan | — | EAZ Chef built their entire brand through influencer cooking events
MARKETING & GROWTH | MG-04 ★ | Google Ads (5 High-Intent Keywords) | Campaign targeting: 'private chef Dubai', 'personal chef UAE', 'chef at home Dubai', 'meal prep chef Dubai', 'home chef service Abu Dhabi'. Budget: AED 3,000–5,000/month. Bilingual ads (Arabic + English). Landing page: chef search page (C-01). Target CPA: AED 150. | P1 | Paid/Marketing | Arabic keyword variants essential for UAE search volume | v0.4 NEW | Not started | — | High-intent keywords convert at booking stage — measurable from day 1
MARKETING & GROWTH | MG-05 ★ | SEO Blog (10 Founding Articles) | 10 articles targeting long-tail queries: 'How much does a private chef cost in Dubai 2026?', 'Best cuisines for private dining in Dubai', 'How to hire a chef for Ramadan UAE', 'Private chef vs restaurant for dinner party'. Arabic language versions. ECJ 16,848-recipe vault as content fuel. | P1 | Web/Content | Arabic articles for Arabic search volume in UAE | v0.4 NEW | Not started | — | 16,848-recipe vault is unmatched SEO content asset vs all competitors
MARKETING & GROWTH | MG-06 ★ | Press Release — UAE Market Launch | Issue launch press release to: Gulf News Food & Drink, Time Out Dubai, What's On UAE, Khaleej Times Business, The National, Lovin Dubai. Angle: 'UAE's only AI-powered private chef marketplace with 16,848-recipe vault and allergen-safe service.' Target 3+ placements. | P1 | Marketing/PR | — | v0.4 NEW | Not done | — | Free earned media; builds brand credibility instantly
MARKETING & GROWTH | MG-07 ★ | Founding Chef Campaign (20 Chefs) | First 20 chefs: 'Founding Chef' badge on profile, 0% commission first 3 bookings, professional photo shoot (ECJ-funded), subdomain URL, featured on homepage. Creates early supply urgency and premium feel. Announced via IG/TikTok launch post. | P0 | Marketing/Ops | Arabic announcement; target hotel-trained chefs in UAE | v0.4 NEW | Not started — launch with chef recruitment | — | Creates supply scarcity narrative and premium positioning at launch
MARKETING & GROWTH | MG-08 ★ | BNI & Professional Network Activation | Aziz activates BNI membership and personal F&B/hospitality network for: (a) chef referrals from hotel/restaurant contacts, (b) corporate event client introductions, (c) investor warm intros. Target: 10 chef leads + 5 client leads within first 2 weeks. Zero cost. | P0 | Founder/Sales | DIFC, Business Bay, JLT professional networks (Aziz's base) | v0.4 NEW | Not started — quick win | — | Highest-ROI channel available before any paid marketing
EatCookJoy UAE ¦ Scope of Work v0.4 ¦ Prepared by Aziz Saif ¦ May 25, 2026

## Open Questions
EatCookJoy UAE — Open Questions & Decisions Required v0.4
# | Question | Section | Impact | Recommended Decision | Owner | Status
OPEN — 13 DECISIONS REQUIRED (sorted by impact)
1 | Commission rate for chefs? | 4.4, OL-02 | HIGH — #1 chef recruitment driver | 20% standard; 15% after 10+ reviews. Publish before chef campaign. | Aziz Saif | ⚠ OPEN
2 | Cancellation protection policy %? | 4.16, C-08 | HIGH — chef retention + legal liability | 100% <24 hrs; 50% 24–48 hrs; 0% >48 hrs (industry standard). | Aziz Saif | ⚠ OPEN
3 | UAE Trade License — free zone or mainland? | OL-01 | HIGH — required for payment + hiring | Evaluate DMCC vs DED mainland. Budget AED 15k–50k. Timeline: 2–4 weeks. | Aziz Saif | ⚠ OPEN
4 | Payment gateway provider? | C-03, OL-04 | HIGH — P0 blocker, no monetisation without | Evaluate Telr vs PayTabs vs Network International. Integration: 4–6 weeks. | Tech Lead | ⚠ OPEN
5 | ECJ group liability insurance vs chef-individual? | OL-06 | HIGH — legal risk before first booking | Require individual upload (4.19) for launch. Add ECJ group policy v2. | Aziz / Legal | ⚠ OPEN
6 | Which documents are REQUIRED vs encouraged? | 4.1, 4.19, OL-05 | HIGH — regulatory risk | REQUIRED: Emirates ID + Food Handler Cert. ENCOURAGED: Freelance license + liability insurance. | Aziz Saif | ⚠ OPEN
7 | Consumer platform spec — who writes it? | C-01 to C-12 | CRITICAL — no demand without it | Start immediately in parallel. Assign product/design resource. Target: 2-week spec. | Aziz Saif | ⚠ OPEN
8 | WhatsApp Business API — account set up? | OL-07, C-04, C-09 | HIGH — all WhatsApp flows depend on it | Register via Meta Business Manager. Apply for green tick. Timeline: 1–2 weeks. | Ops | ⚠ OPEN
9 | Claude AI API scope for 4.14? | 4.14 | MEDIUM — AI Assist feature budget | Define which AI calls are automated. Set monthly API budget. Use Claude 3.5 Haiku. | Tech Lead | ⚠ OPEN
10 | Fast payout UAE bank processing time? | 4.4, DB-05 | MEDIUM — chef satisfaction feature | Confirm T+1 settlement with chosen payment gateway. Typical UAE banks: T+1 business day. | Tech / Finance | ⚠ OPEN
11 | Food handler cert verification — manual or automated? | OL-05, 4.19 | MEDIUM — ops load at scale | Manual for first 50 chefs. Automate via OCR + document AI after that. | Ops | ⚠ OPEN
12 | Search ranking algorithm for C-01? | C-01 | MEDIUM — drives demand conversion | Initial: rating × recency × completeness score. Boost Founding Chefs. | Tech Lead | ⚠ OPEN
13 | Support first tier — human or AI chatbot? | OL-08 | MEDIUM — customer experience | AI chatbot (Arabic + English) for FAQs; human escalation for disputes/allergies. | Ops | ⚠ OPEN
RESOLVED — 7 QUESTIONS ANSWERED IN v0.4
R1 | Public profile routing (4.6) | 4.6 | HIGH | Routes to 'Book' + 'Message first' CTAs. | Product | ✅ RESOLVED
R2 | Is prep schedule chef-editable? (4.3) | 4.3 | MED | Yes, AI default + chef-editable. | Product | ✅ RESOLVED
R3 | Attendee names — mandatory or optional? (4.3) | 4.3 | MED | Guest count mandatory; names optional. | Product | ✅ RESOLVED
R4 | Test client preview vs QA (4.8) | 4.8 | LOW | Chef-facing preview mode only. | Product | ✅ RESOLVED
R5 | In-app messaging vs WhatsApp default (4.9) | 4.9 | HIGH | In-app thread default; WhatsApp as secondary. | Product | ✅ RESOLVED
R6 | Message thread lifespan (4.9) | 4.9 | LOW | 72 hrs post-completion; read-only 30 days; archived. | Product | ✅ RESOLVED
R7 | Recipe servings scaling — v1 or v2? (4.7) | 4.7 | MED | v1 — in build scope. | Product | ✅ RESOLVED
EatCookJoy UAE ¦ Scope of Work v0.4 ¦ Prepared by Aziz Saif ¦ May 25, 2026

## Build Roadmap
EatCookJoy UAE — Build Priority Roadmap v0.4
Phase | Priority | Section | Feature | Platform | Owner | Timeline | Success Metric
Phase 1 — Launch Blockers
Phase 1 — Launch Blockers | P0 | OL-01 | UAE Trade License | Ops | Aziz Saif | Week 1 | License issued
Phase 1 — Launch Blockers | P0 | OL-02 | Publish Chef Commission Rate | Web | Aziz Saif | Week 1 | Rate live on website
Phase 1 — Launch Blockers | P0 | OL-03 | T&C & Privacy Policy (Ar + En) | Web/Legal | Legal + Aziz | Week 1–2 | Both languages live
Phase 1 — Launch Blockers | P0 | OL-04 | IBAN Payment Infrastructure | Tech | Tech Lead | Week 1–3 | Test transaction successful
Phase 1 — Launch Blockers | P0 | OL-07 | WhatsApp Business API Setup | Ops/Tech | Ops | Week 1 | Green tick account live
Phase 1 — Launch Blockers | P0 | OL-05 | Chef Vetting Pipeline | Ops/Web | Ops | Week 2 | First 20 chefs approved
Phase 1 — Launch Blockers | P0 | 4.1 | Sign-in + Onboarding Wizard | iOS/Android | Dev | Week 1–2 | Chef completes onboarding
Phase 1 — Launch Blockers | P0 | 4.2 | Today Home Screen + Allergen Badge | iOS/Android | Dev | Week 2 | Chef sees day at a glance
Phase 1 — Launch Blockers | P0 | 4.3 | Booking Detail (full) | iOS/Android | Dev | Week 2–3 | Chef works full booking flow
Phase 1 — Launch Blockers | P0 | 4.10 | Booking Accept / Decline | iOS/Android | Dev | Week 2 | Chef accepts booking in app
Phase 1 — Launch Blockers | P0 | 4.5 ★ | Ratings & Reviews Display | iOS/Android | Dev | Week 3 | Star rating visible on profile
Phase 1 — Launch Blockers | P0 | 4.15 ★ | Client Rating & Review Trigger | iOS + WhatsApp | Dev | Week 3 | Rating request auto-sends
Phase 1 — Launch Blockers | P0 | C-01 ★ | Consumer: Chef Discovery & Search | Web | Dev | Week 2–4 | Client can browse chefs
Phase 1 — Launch Blockers | P0 | C-02 ★ | Consumer: Booking Flow (8-step) | Web | Dev | Week 2–4 | Test booking end-to-end
Phase 1 — Launch Blockers | P0 | C-03 ★ | Consumer: Payment Gateway | Web | Dev | Week 2–4 | Live card payment processed
Phase 1 — Launch Blockers | P0 | C-04 ★ | Consumer: Booking Confirmations | WhatsApp/Email | Dev | Week 3 | Confirmation within 60 sec
Phase 1 — Launch Blockers | P0 | C-06 ★ | Consumer: Allergen/Dietary Profile | Web | Dev | Week 3 | 11 profiles selectable
Phase 1 — Launch Blockers | P0 | C-07 ★ | Consumer: Review Submission | WhatsApp/Web | Dev | Week 3 | Review submittable by client
Phase 1 — Launch Blockers | P0 | C-08 ★ | Cancellation & Refund Policy Live | Web | Legal/Dev | Week 3 | Policy live at checkout
Phase 1 — Launch Blockers | P0 | C-09 ★ | WhatsApp 'Book a Chef' Button | Web | Dev | Week 1 | Button live, routing to ECJ WA
Phase 1 — Launch Blockers | P0 | MG-01 ★ | Instagram (@eatcookjoyuae) | Social | Marketing | Week 1 | Account live, 3 posts/week
Phase 1 — Launch Blockers | P0 | MG-02 ★ | TikTok (@eatcookjoyuae) | Social | Marketing | Week 1 | Account live, 5 posts/week
Phase 1 — Launch Blockers | P0 | MG-07 ★ | Founding Chef Campaign (20 chefs) | Marketing/Ops | Aziz Saif | Week 2–4 | 20 chefs bookable
Phase 1 — Launch Blockers | P0 | MG-08 ★ | BNI & Network Activation | Sales | Aziz Saif | Week 1 | 5 chef + 3 client leads
Phase 2 — Pre-Beta
Phase 2 — Pre-Beta | P1 | 4.4 | Earnings + Fast Payout Toggle | iOS/Android | Dev | Week 3–5 | Chef views net earnings clearly
Phase 2 — Pre-Beta | P1 | 4.5 ★ | Profile: Video, Badges, Social Links | iOS/Android | Dev | Week 3–5 | Profile completeness >80%
Phase 2 — Pre-Beta | P1 | 4.5 ★ | Chef Pricing / Rate Field | iOS/Android | Dev | Week 3 | Rate visible on public profile
Phase 2 — Pre-Beta | P1 | 4.6 | Public Profile Sharing + Analytics | iOS/Android/Web | Dev | Week 3–5 | Profile shareable via WhatsApp
Phase 2 — Pre-Beta | P1 | 4.9 | Message Client + AI Replies | iOS/Android | Dev | Week 4–5 | Chef-client message in app
Phase 2 — Pre-Beta | P1 | 4.11 | Notifications (12 types) | iOS/Android | Dev | Week 3 | All 12 push types firing
Phase 2 — Pre-Beta | P1 | 4.12 | Settings (full) | iOS/Android | Dev | Week 4 | IBAN set, language toggled
Phase 2 — Pre-Beta | P1 | 4.14 ★ | AI Assist (Menu + Prep + Quote) | iOS/Android | Dev/AI | Week 4–6 | AI generates prep schedule
Phase 2 — Pre-Beta | P1 | 4.16 ★ | Cancellation Protection Display | iOS/Android | Dev | Week 4 | Badge visible on booking detail
Phase 2 — Pre-Beta | P1 | 4.17 ★ | Chef Video Introduction Upload | iOS/Android | Dev | Week 5–6 | Video live on profile
Phase 2 — Pre-Beta | P1 | 4.18 ★ | Pre-Booking Video Call Request | iOS + WhatsApp | Dev | Week 5 | WhatsApp Video CTA working
Phase 2 — Pre-Beta | P1 | 4.19 ★ | Insurance & License Badge | iOS/Android | Dev/Ops | Week 4–5 | 2 badges verified for 10+ chefs
Phase 2 — Pre-Beta | P1 | 4.3 ★ | Dispute / Issue Report | iOS/Android | Dev | Week 5 | Report routes to ops within 2 hrs
Phase 2 — Pre-Beta | P1 | 4.7 ★ | ECJ Recipe Vault Integration | iOS/Android | Dev | Week 4–6 | Chef saves 5+ vault recipes
Phase 2 — Pre-Beta | P1 | OL-06 | Liability Framework Defined | Legal | Aziz/Legal | Week 3 | Policy in T&Cs
Phase 2 — Pre-Beta | P1 | OL-08 ★ | Customer Support (WA + FAQ) | Ops/Web | Ops | Week 3 | <2 hr response SLA live
Phase 2 — Pre-Beta | P1 | OL-09 ★ | Chef Quality Standards Doc | Web/Ops | Aziz | Week 2 | Published on website
Phase 2 — Pre-Beta | P1 | OL-10 ★ | NPS Survey (Post-Service) | WhatsApp/Ops | Ops | Week 4 | NPS >0 in first responses
Phase 2 — Pre-Beta | P1 | C-05 ★ | Client Dashboard | Web | Dev | Week 4–6 | Repeat booking from dashboard
Phase 2 — Pre-Beta | P1 | C-10 ★ | Referral Programme (AED 50) | Web/WhatsApp | Dev | Week 5–6 | First referral booking
Phase 2 — Pre-Beta | P1 | C-11 ★ | Seasonal Landing Pages | Web | Content/Dev | Week 4 | Pages live before next season
Phase 2 — Pre-Beta | P1 | MG-03 ★ | Influencer Campaign (5 micro) | Marketing | Marketing | Week 3–8 | 5 posts, 50K+ impressions
Phase 2 — Pre-Beta | P1 | MG-04 ★ | Google Ads (5 keywords) | Paid | Marketing | Week 3 | AED 3K/mo, >2% CTR
Phase 2 — Pre-Beta | P1 | MG-05 ★ | SEO Blog (10 articles) | Web/Content | Content | Week 3–8 | 10 articles indexed
Phase 2 — Pre-Beta | P1 | MG-06 ★ | Press Release — UAE Launch | PR | Aziz | Week 4–5 | 3+ media placements
Phase 3 — Scale Prep
Phase 3 — Scale Prep | P2 | 4.7 | Recipe Library (full) | iOS/Android | Dev | Month 2 | Chef adds 10+ recipes
Phase 3 — Scale Prep | P2 | 4.8 | Client Preview Mode | iOS/Android | Dev | Month 2 | Preview works in AR + EN
Phase 3 — Scale Prep | P2 | 4.13 | Calendar + Google Sync | iOS/Android | Dev | Month 2 | 0 double-bookings
Phase 3 — Scale Prep | P2 | 4.3 ★ | Recurring Client History | iOS/Android | Dev | Month 2 | Returning client history visible
Phase 3 — Scale Prep | P2 | 4.2 ★ | Earnings Widget on Today | iOS/Android | Dev | Month 2 | Chefs check earnings daily
Phase 3 — Scale Prep | P2 | 4.4 ★ | Earnings PDF Export | iOS/Android | Dev | Month 2 | PDF downloadable
Phase 3 — Scale Prep | P2 | 4.3 ★ | Grocery List Shortcut | iOS/Android | Dev | Month 2 | Chef shares list to WhatsApp
Phase 3 — Scale Prep | P2 | C-12 ★ | Corporate / Event Package Page | Web | Dev/Sales | Month 2 | First corporate booking
Phase 4 — Post-Launch
Phase 4 — Post-Launch | v2 | 4.6 | Chef-Branded Subdomain | Web | Dev | Month 3+ | Top 5 chefs have custom URL
Phase 4 — Post-Launch | v2 | 4.3 | Multi-Proposal / Quote System | iOS/Android | Dev | Month 3+ | Chef sends custom quote
Phase 4 — Post-Launch | v2 | 4.9 | In-App Video Call (WebRTC) | iOS/Android | Dev | Month 4+ | In-app video replaces WhatsApp
Phase 4 — Post-Launch | v2 | 4.3 | Grocery Ordering (Instashop API) | iOS/Android | Dev/Partner | Month 4+ | Chef orders via platform
Phase 4 — Post-Launch | v2 | OL | UAE Startup Funding Application | Ops | Aziz Saif | Month 2–3 | 1 accelerator applied
EatCookJoy UAE ¦ Scope of Work v0.4 ¦ Prepared by Aziz Saif ¦ May 25, 2026

## Summary
EatCookJoy UAE — Scope Dashboard v0.4 ¦ May 2026
Metric | Count | Status
Total Features in Scope | 65 | —
New Features Added (v0.4 ★) | 55 | ✅ Complete
P0 Launch Blockers | 27 | ⚠ Action needed
P1 Pre-Beta Features | 30 | ⚠ Action needed
P2 Scale Prep Features | 7 | —
v2 Post-Launch Features | 1 | —
Open Decisions Required | 13 | ⚠ Action needed
Decisions Resolved (v0.4) | 7 | ✅ Complete
Module | P0 | P1 | P2 | v2 | TOTAL
CHEF APP | 8 | 20 | 6 | 1 | 35
CONSUMER PLATFORM | 8 | 3 | 1 | 0 | 12
OPS & LEGAL | 7 | 3 | 0 | 0 | 10
MARKETING & GROWTH | 4 | 4 | 0 | 0 | 8
PRIORITY KEY
P0 — Launch Blocker: Complete before first live booking
P1 — Pre-Beta: Complete before opening to first 50 clients
P2 — Scale Prep: Complete before growing beyond 20 chefs / 50 bookings
v2 — Post-Launch: Roadmap items after first 3 months live
★ — New feature added in v0.4 (not in original v0.1–v0.3 design spec)
EatCookJoy UAE ¦ Scope of Work v0.4 ¦ Prepared by Aziz Saif ¦ May 25, 2026